## Gantt Schedule
UNICORE : CAMPUS OPERATING PLATFORM
12-Week High-Concurrency Relational Engineering Lifecycle & Master Gantt Schedule
Institution: Thapar Institute of Engineering & Technology ¦ Scale: 30,000+ Students ¦ Core Stack: PostgreSQL (BCNF), Tezz/Express, React, Cloudflare
| TOTAL DURATION |  |  |  | TARGET SCALE |  |  |  | CONCURRENCY TARGET |  |  |  | RELATIONAL INTEGRITY |  |  |  | OVERALL PROGRESS
| 12 Weeks (84 Days) |  |  |  | 30,000+ Active Students |  |  |  | 2,500+ Peak TPS |  |  |  | 8 BCNF Schemas ¦ 35+ Tables |  |  |  | 100% (Complete)
WBS | Task Description & Deliverables | Phase / Domain | Lead Owner | Start Date | End Date | Days | Progress | Status | Predec. | 12-WEEK ENGINEERING SPRINT TIMELINE (WEEKS 1 — 12)
[10 empty] | W1 Jan 05 | W2 Jan 12 | W3 Jan 19 | W4 Jan 26 | W5 Feb 02 | W6 Feb 09 | W7 Feb 16 | W8 Feb 23 | W9 Mar 02 | W10 Mar 09 | W11 Mar 16 | W12 Mar 23
1.0 | PHASE 1: KERNEL ARCHITECTURE & SCHEMA DESIGN | Kernel | Core Engineering Team | 2026-01-05 | 2026-01-25 | 21 | 100% | Completed | — | ████ | ████ | ████
1.1 | Domain Modeling & Scope Boundary Elicitation (8 Domains) | Academic/Hostel | Ankit Rath (1024030458) | 2026-01-05 | 2026-01-11 | 7 | 100% | Completed | — | 100%
1.2 | Entity-Relationship (ER) Modeling across 8 Schemas | Kernel | Ankit Rath (1024030458) | 2026-01-09 | 2026-01-16 | 8 | 100% | Completed | 1.1 | 100% | 100%
1.3 | Normalization Proof (1NF, 2NF, 3NF, BCNF Decomp) | Kernel Theory | Abhinav Kumar Singh (1024030440) | 2026-01-12 | 2026-01-20 | 9 | 100% | Completed | 1.2 |  | 100% | 100%
1.4 | PostgreSQL DDL Generation (35+ Tables, FKs, Checks) | Kernel DDL | Core Engineering Team | 2026-01-16 | 2026-01-23 | 8 | 100% | Completed | 1.3 |  | 100% | 100%
1.5 | Synthetic Dataset Pipeline (30,000+ Mock Records) | Database | Manan Kapoor (1024030467) | 2026-01-20 | 2026-01-25 | 6 | 100% | Completed | 1.4 |  |  | 100%
M1 | ◆ MILESTONE 1: Stage 1 Architecture & BCNF DDL Approved | Stage Milestone | Faculty Evaluation Board | 2026-01-25 | 2026-01-25 | 1 | 100% | Achieved | 1.5 |  |  | ◆
2.0 | PHASE 2: THE CONCURRENCY LAYER & RELATIONAL SAFEGUARDS | Concurrency | Core Engineering Team | 2026-01-26 | 2026-02-15 | 21 | 100% | Completed | M1 |  |  |  | ████ | ████ | ████
2.1 | Pessimistic Row-Level Locking (SELECT FOR UPDATE) | Transactions | Ankit Rath (1024030458) | 2026-01-26 | 2026-02-02 | 8 | 100% | Completed | M1 |  |  |  | 100%
2.2 | Advisory Lock Engine (Hostel Bed & Elective Allocation) | Locking Engine | Abhinav Kumar Singh (1024030440) | 2026-01-30 | 2026-02-06 | 8 | 100% | Completed | 2.1 |  |  |  | 100% | 100%
2.3 | Automated PL/SQL Triggers (BEFORE/AFTER Mutation Checks) | PL/SQL Triggers | Ankit Rath (1024030458) | 2026-02-03 | 2026-02-10 | 8 | 100% | Completed | 2.2 |  |  |  |  | 100%
2.4 | Immutable JSON Forensic Audit Logging & Audit Ledger | Forensic Audit | Manan Kapoor (1024030467) | 2026-02-07 | 2026-02-13 | 7 | 100% | Completed | 2.3 |  |  |  |  | 100% | 100%
2.5 | pgbench Setup, Multi-Threaded Stress Testing (Deadlock Check) | Stress Test | Core Engineering Team | 2026-02-09 | 2026-02-15 | 7 | 100% | Completed | 2.4 | [5 empty] | 100%
M2 | ◆ MILESTONE 2: Stage 2 Concurrency & Transaction Safeguards Verified | Stage Milestone | Faculty Evaluation Board | 2026-02-15 | 2026-02-15 | 1 | 100% | Achieved | 2.5 | [5 empty] | ◆
3.0 | PHASE 3: REST API GATEWAY, RBAC & CI/CD DEVOPS | API & DevOps | Core Engineering Team | 2026-02-16 | 2026-03-08 | 21 | 100% | Completed | M2 | [6 empty] | ████ | ████ | ████
3.1 | High-Throughput REST Gateway & Micro-Router Architecture | Backend API | Manan Kapoor (1024030467) | 2026-02-16 | 2026-02-23 | 8 | 100% | Completed | M2 | [6 empty] | 100%
3.2 | Role-Based Access Control (RBAC), JWT & Refresh Tokens | Auth Security | Abhinav Kumar Singh (1024030440) | 2026-02-20 | 2026-02-27 | 8 | 100% | Completed | 3.1 | [6 empty] | 100% | 100%
3.3 | LibSQL Cloud Replication & Cloudflare Edge Worker Deployment | Cloud Edge | Abhinav Kumar Singh (1024030440) | 2026-02-24 | 2026-03-03 | 8 | 100% | Completed | 3.2 | [7 empty] | 100% | 100%
3.4 | Automated Unit, Integration & ACID Concurrency Regression Tests | QA Testing | Core Engineering Team | 2026-02-27 | 2026-03-06 | 8 | 100% | Completed | 3.3 | [7 empty] | 100% | 100%
3.5 | GitHub Actions CI/CD Pipeline (deploy.yml) & Docker Compose | DevOps / CI | Manan Kapoor (1024030467) | 2026-03-02 | 2026-03-08 | 7 | 100% | Completed | 3.4 | [8 empty] | 100%
M3 | ◆ MILESTONE 3: Stage 3 API Gateway & Cloud Worker Live | Stage Milestone | Faculty Evaluation Board | 2026-03-08 | 2026-03-08 | 1 | 100% | Achieved | 3.5 | [8 empty] | ◆
4.0 | PHASE 4: FRONTEND SHELL, UX, STAMPEDE SIMULATION & DEFENSE | Frontend / Eval | Core Engineering Team | 2026-03-09 | 2026-03-29 | 21 | 100% | Completed | M3 | [9 empty] | ████ | ████ | ████
4.1 | React + Vite + Tailwind CSS Shell & Modern Design Tokens | Frontend UI | Abhinav Kumar Singh (1024030440) | 2026-03-09 | 2026-03-16 | 8 | 100% | Completed | M3 | [9 empty] | 100%
4.2 | Role Dashboards: Student (Abhinav), Faculty, Admin, Staff | Frontend UX | Abhinav Kumar Singh (1024030440) | 2026-03-13 | 2026-03-20 | 8 | 100% | Completed | 4.1 | [9 empty] | 100% | 100%
4.3 | End-to-End 'Elective Rush' Stampede Simulation (30,000 Users) | Simulation | Manan Kapoor (1024030467) | 2026-03-17 | 2026-03-24 | 8 | 100% | Completed | 4.2 | [10 empty] | 100% | 100%
4.4 | Benchmarking Validation (2,500+ TPS, <50ms p95, <2h TTA) | Evaluation | Core Engineering Team | 2026-03-20 | 2026-03-27 | 8 | 100% | Completed | 4.3 | [10 empty] | 100% | 100%
4.5 | Stage 3 Technical Master Report & LaTeX Documentation | Documentation | Core Engineering Team | 2026-03-23 | 2026-03-29 | 7 | 100% | Completed | 4.4 | [11 empty] | 100%
M4 | ◆ MILESTONE 4: Final Project Submission & Institutional Defense | Project Defense | Faculty Evaluation Board | 2026-03-29 | 2026-03-29 | 1 | 100% | Achieved | 4.5 | [11 empty] | ◆

## Milestones & Benchmarks
UNICORE : FORMAL STAGE MILESTONES & BENCHMARK VALIDATION
1. FORMAL STAGE MILESTONES BREAKDOWN
Stage Code | Milestone Title | Target Milestone Date | Primary Deliverables | Acceptance Criteria | Responsible Lead | Status
Stage 1 | Project Proposal & BCNF DDL | 2026-01-25 (Week 3) | 8 ER Schemas, Normalization Proofs (1NF to BCNF), PostgreSQL DDL | 100% Determinants Candidate Keys; Zero Partial/Transitive Dependencies | Abhinav Kumar / Ankit Rath | Approved
Stage 2 | Prototype & Concurrency Guard | 2026-02-15 (Week 6) | SELECT FOR UPDATE Locks, PL/SQL Triggers, Forensic JSON Audit Log | Zero double-allocations during 1,000 concurrent room booking requests | Ankit Rath / Abhinav Kumar | Verified
Stage 3 | API Gateway & Edge Deployment | 2026-03-08 (Week 9) | REST API, RBAC JWT Rotation, Cloudflare Worker, GitHub Actions CI | End-to-end automated tests pass; JWT token revoked within <50ms | Manan Kapoor / Abhinav Kumar | Deployed
Final Stage | Technical Master Report & Defense | 2026-03-29 (Week 12) | React UX Shell, Elective Stampede Simulation, LaTeX Master Report | 2,500+ sustained TPS; p95 latency <50ms; TTA <= 2 hours | Full Project Team | Ready for Defense
2. QUANTITATIVE BENCHMARKING TARGETS VS MEASURED RESULTS
Metric Code | Benchmarking Parameter | Institutional Target | Measured Production Result | Target Scale / Conditions | Validation Test Methodology | Compliance
KPI-01 | Peak Transaction Throughput (TPS) | >= 2,500 TPS | 2,840 TPS | Simulated 30,000 student rush | pgbench + wrk load runner | EXCEEDED
KPI-02 | p95 Query Latency | <= 50 ms | 38.4 ms | Under 2,000 concurrent req/sec | APM distributed tracing | SATISFIED
KPI-03 | p99 Maximum Latency | <= 120 ms | 89.2 ms | Peak elective registration spike | Cloudflare edge metrics | SATISFIED
KPI-04 | Time-To-Acknowledgement (TTA) | <= 2.0 Hours | < 15 Minutes | Instant multi-domain cascade | Forensic timestamp delta | EXCEEDED
KPI-05 | Database Deadlocks Encountered | 0 Deadlocks | 0 Deadlocks | Multi-table concurrent bookings | Strict lock-ordering protocol | SATISFIED
KPI-06 | ACID Compliance Rate | 100.0% | 100.0% | 30,000+ atomic state transfers | Automated mutation tests | SATISFIED
KPI-07 | Audit Trail Completeness | 100.0% | 100.0% Immutable | All financial & bed allocations | Cryptographic hash check | SATISFIED

## Team RACI Matrix
UNICORE : TEAM RACI RESPONSIBILITY ASSIGNMENT MATRIX
Legend: R = Responsible (Does the work) ¦ A = Accountable (Approver) ¦ C = Consulted (Provides input) ¦ I = Informed (Kept updated)
WBS | Work Breakdown Task & Deliverable | Abhinav Kumar Singh (1024030440) | Ankit Rath (1024030458) | Manan Kapoor (1024030467) | Faculty Guide / Evaluation Board | Primary Domain
1.1 | Domain Modeling & Entity Scope Boundaries | C | R / A | C | I | Kernel
1.2 | Entity-Relationship (ER) Modeling (8 Schemas) | C | R / A | C | I | Kernel
1.3 | Normalization Proof (1NF, 2NF, 3NF, BCNF) | R / A | C | C | I | Kernel Theory
1.4 | PostgreSQL DDL Scripts (35+ Tables, FKs, Checks) | R | R | A | I | Kernel DDL
1.5 | Synthetic Dataset Pipeline (30,000+ Mock Records) | C | C | R / A | I | Database
M1 | Stage 1 Architecture & BCNF DDL Approval | R | R | R | A | Milestone 1
2.1 | Row-Level Locking Engine (SELECT FOR UPDATE) | C | R / A | C | I | Concurrency
2.2 | Advisory Lock Architecture (Hostel & Courses) | R / A | C | C | I | Locking Engine
2.3 | Automated PL/SQL Triggers (Balance/Seat Safeguards) | C | R / A | C | I | PL/SQL
2.4 | Immutable JSON Forensic Audit Logging | C | C | R / A | I | Forensic Audit
2.5 | pgbench Concurrency & Deadlock Stress Testing | R | A | R | I | Stress Test
M2 | Stage 2 Prototype & Concurrency Safeguards Verified | R | R | R | A | Milestone 2
3.1 | REST API Gateway & Micro-Router Implementation | C | C | R / A | I | Backend API
3.2 | Role-Based Access Control (RBAC), JWT & Refresh Tokens | R / A | C | C | I | Auth Security
3.3 | LibSQL Database Replication & Cloudflare Workers | R / A | C | C | I | Cloud Edge
3.4 | Automated Unit, Integration & Concurrency Tests | R | R | R / A | I | QA Testing
3.5 | GitHub Actions CI/CD (deploy.yml) & Docker Compose | C | C | R / A | I | DevOps / CI
M3 | Stage 3 API Gateway & Cloud Deployment Live | R | R | R | A | Milestone 3
4.1 | React + Vite + Tailwind CSS Shell & Design Tokens | R / A | C | C | I | Frontend UI
4.2 | Role Portals: Student, Faculty, Admin, Staff | R / A | C | C | I | Frontend UX
4.3 | End-to-End 'Elective Rush' Stampede Simulation | C | C | R / A | I | Simulation
4.4 | Benchmarking Validation (2,500+ TPS, <50ms p95) | R | R | R / A | I | Evaluation
4.5 | Stage 3 Technical Master Report & LaTeX Documentation | R | R | R | A | Documentation
M4 | Final Project Submission & Institutional Defense | R | R | R | A | Milestone 4

## Risk Management
UNICORE : RISK ANALYSIS & CONTINGENCY MITIGATION MATRIX
Risk ID | Risk Category | Potential Failure Mode / Threat | Severity | Likelihood | Technical Mitigation Strategy | Residual Risk Status
RSK-01 | Database | Deadlocks during concurrent elective registration rush | Critical | High | Enforce strict lexicographical lock ordering across PL/SQL procedures; fallback transaction retries with exponential backoff. | Mitigated (Zero Deadlocks)
RSK-02 | Data Integrity | Double allocation of hostel bed rooms under concurrent POST requests | Critical | High | Row-level pessimistic locking (SELECT FOR UPDATE) coupled with Postgres UNIQUE partial index constraints on active allocations. | Mitigated (Verified)
RSK-03 | Data Migration | Data loss or schema corruption when migrating legacy records | High | Medium | Staging dual-write pipeline with strict BCNF foreign-key validation and automated checksum audits prior to cutover. | Controlled (Staged)
RSK-04 | Security | Unauthorized access & student PII leakage through broken endpoint authorization | High | Medium | Stateless cryptographic JWT tokens with mandatory IP/device fingerprinting, 15-minute expiration, and RBAC middleware. | Mitigated (Secured)
RSK-05 | Performance | Traffic stampede degrading database response time beyond 200ms | High | High | Cloudflare edge caching for read-heavy portals; connection pooling with pgbouncer; sub-50ms index optimizations. | Mitigated (38ms p95)
RSK-06 | Availability | Single-point-of-failure in centralized database node | High | Low | Replicated read-replicas across edge workers; continuous streaming WAL archive backups to Turso LibSQL cloud instances. | Controlled (HA Enabled)